## 週報
週報
1. プロジェクトの一般情報
プロジェクト名 |  |  |  |  | 案件名
PM担当者名 |  |  |  |  | 管理者 |  | プロジェクト開始日 |  | YYYY/MM/DD
報告日 |  |  |  |  | YYYY/MM/DD | 報告期間 | YYYY/MM/DD | ～ | YYYY/MM/DD
2.全体概況
2.1進捗概況
■進捗：
2022年09月06日まで全体案件のXX.XX%完了しております。作業はスケジュールの通りに3日間ぐらい遅延があります。各工程の状況は以下の通りです。
|  |  |  | Specs |  | 83% 完了しております。
|  |  |  | Coding |  | 87.3% 完了しております。
|  |  |  | Integration Task |  | 88.9% 完了しております。
|  |  |  | UT Checklist |  | 100.0% 完了しております。
|  |  |  | Execute UT Checklist |  | 63%しています。
■原因
リリースした後、指摘や不良と要望を対応する原因です。
■対策
リソースを1名追加しました。
→目標は９月２１日週まで遅延分はリカバリーできるようにします。
2.2.品質概況
単体テストチェックリストはたりないですので、観点を追加してチェックリスト追加いたします。
3.詳細状況
3.1進捗概況
|  | # | 工程 |  |  | タスク件数(全) | 完了予定 | 完了実績 | %Plan | %Actual
|  | 1 | Specs |  |  | 6 | 6 | 5 | 100% | 83.33%
|  | 2 | Coding |  |  | 71 | 71 | 62 | 100% | 87.32%
|  | 3 | Integration Task |  |  | 72 | 72 | 64 | 100% | 88.89%
|  | 4 | UT Checklist |  |  | 72 | 36 | 72 | 50% | 100%
|  | 5 | Execute UT Checklist |  |  | 72 | 36 | 45 | 50% | 62.5%
3.2.SKG内品質概況
チェックリスト実行状況
|  | # | 項目 |  |  | 全チェック(件数) | チェック済み(件数) | 済み(％)
|  | 1 | チェックリスト |  |  | 4346 | 2884 | 66.36%
バグ状況
|  | # | 項目 |  |  | 発見(件数) | 修正済み(件数) | 済み(％)
|  | 1 | バグ |  |  | 283 | 201 | 71.02%
→品質評価した後、対策追加いたします。
3.3.お客様指摘状況
|  | # | 項目 |  | 区分 | 全件数 | 新規 | 対応中 | 対応済 | キャンセル | 終了
|  | 1 | AAA機能 |  | CR | 5 | 3 | 2 | 0.01 | 1 | 1
|  | 1 |  |  | バグ | 12 | 5 | 3 | 0.01 | 2 | 2
|  | 1 |  |  | 質問 | 2 | 1 | 0 | 0 | 0 | 1
3.4.質問
|  | # | 項目 |  |  | 全体累計件数 | 回答済み | 残り | 完了率（％）
|  | 1 | 質問 |  |  | 197 | 183 | 14 | 92.89%
優先高質問を回答お願いします。
6.その他
6.1 問題１：
問題または要望にはここに記述します。
6.2 問題2：
問題または要望にはここに記述します。
例

## 01.詳細日程
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
# | 中作業 | 担当 | 開始日(StartDate) |  | 完了日(EndDate) |  | ケース数 実績 | 消化数 | 消化率 | バグ発見 | バグ修正 | 状況 | 備考 | Check late
| (MediumTask) | (PIC) | 予定(Plan) | 実績(Actual) | 予定(Plan) | 実績(Actual) |  |  | % |  |  | Status | Note | <auto>
Create Spec Task
1 | (Specs)「自己評価の入力」の評価項目は科目に紐づいていた評価項目を表示していたが、科目ークラスに紐づいた評価項目を表示する。 | ABC | 2022-08-08 | 2022-08-03 | 2022-08-10 | 2022-08-04 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
2 | (Specs)授業アンケート機能について | ABC | 2022-08-11 | 2022-08-04 | 2022-08-15 | 2022-08-05 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
3 | (Specs)【-352】管理者:教員の学生デフォルト設定 | ABC | 2022-08-16 | 2022-08-05 | 2022-08-19 | 2022-08-08 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
4 | (Specs)【-353】管理者:職員の学生デフォルト設定 | ABC | 2022-08-08 | 2022-08-08 | 2022-08-09 | 2022-08-09 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
5 | (Specs)バッチ処理の変更・追加処理 | ABC | 2022-08-10 | 2022-08-10 | 2022-08-10 | 2022-08-10 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
6 | (Specs)「2達成度の確認」でバッチ処理している計算方法を積み上げ式計算に変更する。 | ABC | 2022-08-11 |  | 2022-08-15 | [6 empty] | 2 ¦ 作業中 / In Progress |  | Late
Coding Task
7 | [CD][バッチ詳細] 1 ms_student.csv | TBD | 2022-08-03 | 2022-08-03 | 2022-08-04 | 2022-08-04 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
8 | [CD][バッチ詳細] 2 ms_teacher.csv | TBD | 2022-08-04 | 2022-08-04 | 2022-08-05 | 2022-08-05 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
9 | [CD][バッチ詳細] 3 ms_supervisor.csv | TBD | 2022-08-05 | 2022-08-05 | 2022-08-08 | 2022-08-08 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
10 | [CD][バッチ詳細] 4 ms_subject.csv | TBD | 2022-08-08 | 2022-08-08 | 2022-08-09 | 2022-08-09 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
11 | [CD][バッチ詳細] 5 ms_school_record.csv | TBD | 2022-08-10 | 2022-08-10 | 2022-08-10 | 2022-08-10 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
12 | [CD][バッチ詳細] 6 ms_school_record_failure.csv | TBD | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-08-11 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
13 | [CD][バッチ詳細] 7 ms_school_record_gpa.csv | TBD | 2022-08-12 | 2022-08-12 | 2022-08-12 | 2022-08-12 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
14 | [CD][バッチ詳細] 8 ms_jikanwari.csv | TBD | 2022-08-15 | 2022-08-15 | 2022-08-15 | 2022-08-15 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
15 | [CD][バッチ詳細] 9 ms_attendance_management.csv | TBD | 2022-08-16 | 2022-08-16 | 2022-08-16 | 2022-08-16 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
16 | [CD][バッチ詳細] 10 圧縮 | TBD | 2022-08-17 | 2022-08-17 | 2022-08-17 | 2022-08-17 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
17 | [CD][バッチ詳細] 11 容量チェック | TBD | 2022-08-18 | 2022-08-18 | 2022-08-18 | 2022-08-18 | [5 empty] | 6 ¦ キャンセル / Canceled |  | Done
18 | [CD][バッチ詳細] 12 ファイル転送 | TBD | 2022-08-19 | 2022-08-19 | 2022-08-19 | 2022-08-19 | [5 empty] | 6 ¦ キャンセル / Canceled |  | Done
19 | [CD][バッチ詳細] 13 プロセス残留チェック | TBD | 2022-08-22 | 2022-08-22 | 2022-08-22 | 2022-08-22 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
20 | [CD][バッチ詳細] 14 tr_student_monthly_belongsテーブルのデータ保存を実行 | TBD | 2022-08-23 | 2022-08-23 | 2022-08-23 | 2022-08-23 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
21 | [CD][バッチ詳細] 15 日ごとにアクセスする学生の総数を記録 | TBD | 2022-08-24 | 2022-08-24 | 2022-08-24 | 2022-08-24 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
22 | [CD][バッチ詳細]「2達成度の確認」でバッチ処理している計算方法を積み上げ式計算に変更する。 | TBD | 2022-08-25 | 2022-08-26 | 2022-08-25 | 2022-08-26 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
23 | [CD][バッチ詳細]バッチ処理の変更・追加処理 | TBD | 2022-08-29 | 2022-08-31 | 2022-08-29 | 2022-08-31 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
24 | [CD][API]95-1 アンケート詳細取得 | TBD | 2022-08-01 | 2022-08-01 | 2022-08-01 | 2022-08-01 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
25 | [CD][API]95-2 アンケート情報保存 | TBD | 2022-08-01 | 2022-08-01 | 2022-08-01 | 2022-08-01 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
26 | [CD][API]95-3 アンケート情報更新 | TBD | 2022-08-01 | 2022-08-01 | 2022-08-01 | 2022-08-01 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
27 | [CD][API]160-1 管理者のシステム情報を取得 | TBD | 2022-08-01 | 2022-08-01 | 2022-08-01 | 2022-08-01 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
28 | [CD][API]160-2 管理者情報を取得 | TBD | 2022-08-02 | 2022-08-02 | 2022-08-02 | 2022-08-02 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
29 | [CD][API]123-6 学生編集 | TBD | 2022-08-02 | 2022-08-02 | 2022-08-02 | 2022-08-02 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
30 | [CD][API]128-1 一般ユーザー情報 | TBD | 2022-08-03 | 2022-08-03 | 2022-08-03 | 2022-08-03 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
31 | [CD][API]128-2 一般ユーザー削除 | TBD | 2022-08-03 | 2022-08-03 | 2022-08-03 | 2022-08-03 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
32 | [CD][API]128-3 複数一般ユーザー削除 | TBD | 2022-08-04 | 2022-08-04 | 2022-08-04 | 2022-08-04 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
33 | [CD][API]128-4 一般ユーザーCSVインポート | TBD | 2022-08-04 | 2022-08-04 | 2022-08-04 | 2022-08-04 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
34 | [CD][API]128-5 一般ユーザーCSVエクスポート | TBD | 2022-08-05 | 2022-08-05 | 2022-08-05 | 2022-08-05 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
35 | [CD][API]128-6 一般ユーザー情報追加 | TBD | 2022-08-05 | 2022-08-05 | 2022-08-05 | 2022-08-05 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
36 | [CD][API]128-7 一般ユーザー情報更新 | TBD | 2022-08-08 | 2022-08-08 | 2022-08-08 | 2022-08-08 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
37 | [CD][API]129-1 教員に管理される学生一覧取得 | TBD | 2022-08-08 | 2022-08-08 | 2022-08-08 | 2022-08-08 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
38 | [CD][API]129-2 管理者一覧取得 | TBD | 2022-08-09 | 2022-08-09 | 2022-08-09 | 2022-08-09 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
39 | [CD][API]129-3 管理者登録 | TBD | 2022-08-09 | 2022-08-09 | 2022-08-09 | 2022-08-09 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
40 | [CD][API]129-4 管理者更新 | TBD | 2022-08-10 | 2022-08-10 | 2022-08-10 | 2022-08-10 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
41 | [CD][API]129-5 管理者削除 | TBD | 2022-08-10 | 2022-08-10 | 2022-08-10 | 2022-08-10 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
42 | [CD][API]129-6 管理者CSVインポート | TBD | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-08-11 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
43 | [CD][API]129-7 管理者CSVエクスポート | TBD | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-08-11 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
44 | [CD][API]131-1 ms_teacher_authorities一覧取得 | TBD | 2022-08-12 | 2022-08-12 | 2022-08-12 | 2022-08-12 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
45 | [CD][API]131-2 ms_teacher_authorities情報追加 | TBD | 2022-08-12 | 2022-08-12 | 2022-08-12 | 2022-08-12 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
46 | [CD][API]131-3 ms_teacher_authorities情報更新 | TBD | 2022-08-15 | 2022-08-15 | 2022-08-15 | 2022-08-15 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
47 | [CD][API]131-4 ms_teacher_authorities情報削除 | TBD | 2022-08-15 | 2022-08-15 | 2022-08-15 | 2022-08-15 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
48 | [CD][API]131-5 ms_teacher_authorities情報CSVインポート | TBD | 2022-08-02 | 2022-08-02 | 2022-08-02 | 2022-08-02 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
49 | [CD][API]131-6 ms_teacher_authorities情報CSVエクスポート | TBD | 2022-08-02 | 2022-08-02 | 2022-08-02 | 2022-08-02 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
50 | [CD][API]148-1 学習・教育到達目標積み上げ式の一覧取得 | TBD | 2022-08-03 | 2022-08-03 | 2022-08-03 | 2022-08-03 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
51 | [CD][API]148-2 学習・教育到達目標積み上げ式追加 | TBD | 2022-08-03 | 2022-08-03 | 2022-08-03 | 2022-08-03 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
52 | [CD][API]148-3 学習・教育到達目標積み上げ式更新 | TBD | 2022-08-04 | 2022-08-04 | 2022-08-04 | 2022-08-04 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
53 | [CD][API]148-1 学習・教育達成目標計算設定の一覧取得 | TBD | 2022-08-04 | 2022-08-04 | 2022-08-04 | 2022-08-04 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
54 | [CD][API]148-2 学習・教育達成目標計算設定追加 | TBD | 2022-08-05 | 2022-08-05 | 2022-08-05 | 2022-08-05 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
55 | [CD][API]148-3 学習・教育達成目標計算設定更新 | TBD | 2022-08-05 | 2022-08-05 | 2022-08-05 | 2022-08-05 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
56 | [CD][API]148-4 学習・教育達成目標計算設定削除 | TBD | 2022-08-08 | 2022-08-08 | 2022-08-08 | 2022-08-08 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
57 | [CD][API]148-5 学習・教育達成目標計算設定削除 | TBD | 2022-08-08 | 2022-08-08 | 2022-08-08 | 2022-08-08 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
58 | [CD][API]148-6 学習・教育達成目標計算設定CSVインポート | TBD | 2022-08-09 | 2022-08-09 | 2022-08-09 | 2022-08-09 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
59 | [CD][API]148-7 学習・教育達成目標計算設定CSVエクスポート | TBD | 2022-08-09 | 2022-08-09 | 2022-08-09 | 2022-08-09 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
60 | [CD][API]149-1 学習・教育達成目標授業科目計算設定の一覧取得 | TBD | 2022-08-10 | 2022-08-10 | 2022-08-10 | 2022-08-10 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
61 | [CD][API]149-2 学習・教育達成目標授業科目計算設定追加 | TBD | 2022-08-10 | 2022-08-10 | 2022-08-10 | 2022-08-10 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
62 | [CD][API]149-3 学習・教育達成目標授業科目計算設定更新 | TBD | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-08-11 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
63 | [CD][API]149-4 学習・教育達成目標授業科目計算設定削除 | TBD | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-08-11 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
64 | [CD][API]149-5 学習・教育達成目標授業科目計算設定削除 | TBD | 2022-08-12 | 2022-08-12 | 2022-08-12 | 2022-08-12 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
65 | [CD][API]149-6 学習・教育達成目標授業科目計算設定CSVインポート | TBD | 2022-08-12 | 2022-08-12 | 2022-08-12 | 2022-08-12 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
66 | [CD][API]149-7 学習・教育達成目標授業科目計算設定CSVエクスポート | TBD | 2022-08-15 | 2022-08-15 | 2022-08-15 | 2022-08-15 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
67 | [CD][API]154-1 学生デフォルトモジュール設定取得 | TBD | 2022-08-15 | 2022-09-06 | 2022-08-15 | [6 empty] | 2 ¦ 作業中 / In Progress |  | Late
68 | [CD][API]154-2 学生のCVSデフォルトモジュール設定エクスポート | TBD | 2022-09-06 |  | 2022-09-08 | [6 empty] | 1¦ 新しい / New |  | Late
69 | [CD][API]155-1 学生を閲覧する教員のデフォルトレイアウトを取得 | TBD | 2022-09-06 |  | 2022-09-08 | [6 empty] | 1¦ 新しい / New |  | Late
70 | [CD][API]155-2 授業アンケート - 公開データを格納 | TBD | 2022-09-06 |  | 2022-09-08 | [6 empty] | 1¦ 新しい / New |  | Late
71 | [CD][API]「自己評価の入力」の評価項目は科目に紐づいていた評価項目を表示していたが、科目ークラスに紐づいた評価項目を表示する。 | TBD | 2022-09-06 |  | 2022-09-08 | [6 empty] | 1¦ 新しい / New |  | Late
72 | [CD][API]授業アンケート機能について | TBD | 2022-08-16 | 2022-08-16 | 2022-09-06 | 2022-08-17 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
73 | [CD][API]【-352】管理者:教員の学生デフォルト設定 | TBD | 2022-09-08 |  | 2022-09-12 | [6 empty] | 1¦ 新しい / New |  | Late
74 | [CD][API]【-353】管理者:職員の学生デフォルト設定 | TBD | 2022-09-08 |  | 2022-09-12 | [6 empty] | 1¦ 新しい / New |  | Late
75 | [CD][API]95-4 授業アンケート - 公開データを格納 | TBD | 2022-08-24 | 2022-08-24 | 2022-08-24 | 2022-08-24 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
76 | [CD][API]95-5 授業アンケート - 公開データを作成 | TBD | 2022-08-18 | 2022-08-18 | 2022-08-18 | 2022-09-05 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
77 | [CD][API]95-6 授業アンケート - 公開データを削除 | TBD | 2022-08-19 | 2022-08-19 | 2022-08-19 | 2022-09-05 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
Intergration Task |  | TBD
78 | 【-170】(APIの組み込み)教員・職員：今学期の学びの目標 | TBD | 2022-08-01 | 2022-08-01 | 2022-08-01 | 2022-08-01 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
79 | 【-171】(APIの組み込み)教員・職員：自分の中に描く将来像 | TBD | 2022-08-01 | 2022-08-01 | 2022-08-01 | 2022-08-01 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
80 | 【-172】(APIの組み込み)教員・職員：学生生活、サークルなど | TBD | 2022-08-02 | 2022-08-02 | 2022-08-02 | 2022-08-02 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
81 | 【-173】(APIの組み込み)教員・職員：教員からのコメント（学生へのコメント） | TBD | 2022-08-02 | 2022-08-02 | 2022-08-02 | 2022-08-02 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
82 | 【-174】(APIの組み込み)教員・職員：指導教員名／面談日 | TBD | 2022-08-03 | 2022-08-03 | 2022-08-03 | 2022-08-03 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
83 | 【-175】(APIの組み込み)教員・職員：GPA・TOEIC・出欠状況 | TBD | 2022-08-03 | 2022-08-03 | 2022-08-03 | 2022-08-03 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
84 | 【-176】(APIの組み込み)教員・職員：履修情報 | TBD | 2022-08-04 | 2022-08-04 | 2022-08-04 | 2022-08-04 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
85 | 【-177】(APIの組み込み)教員・職員：履修情報-自己評価・授業アンケート | TBD | 2022-08-04 | 2022-08-04 | 2022-08-04 | 2022-08-04 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
86 | 【-178】(APIの組み込み)教員・職員：履修状況の確認 | TBD | 2022-08-05 | 2022-08-05 | 2022-08-05 | 2022-08-05 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
87 | 【-179】(APIの組み込み)教員・職員：履修状況の確認-自己評価・授業アンケート | TBD | 2022-08-05 | 2022-08-05 | 2022-08-05 | 2022-08-05 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
88 | 【-180】(APIの組み込み)教員・職員：達成度の確認-学習・教育到達目標による成績の状況 (成績平均) | TBD | 2022-08-08 | 2022-08-08 | 2022-08-08 | 2022-08-08 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
89 | 【-181】(APIの組み込み)教員・職員：達成度の確認-学習・教育到達目標による自己評価の状況 (達成度) | TBD | 2022-08-08 | 2022-08-08 | 2022-08-08 | 2022-08-08 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
90 | 【-182】(APIの組み込み)教員・職員：達成度の確認-学習・教育到達目標の達成度 | TBD | 2022-08-09 | 2022-08-09 | 2022-08-09 | 2022-08-09 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
91 | 【-183】(APIの組み込み)教員・職員：TOEIC | TBD | 2022-08-09 | 2022-08-09 | 2022-08-09 | 2022-08-09 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
92 | 【-186】(APIの組み込み)教員・職員・管理者：担当学生一覧 | TBD | 2022-08-10 | 2022-08-10 | 2022-08-10 | 2022-08-10 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
93 | 【-187】(APIの組み込み)教員・職員・管理者：担当学生一覧-教職間メモ | TBD | 2022-08-10 | 2022-08-10 | 2022-08-10 | 2022-08-10 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
94 | 【-196】(APIの組み込み)職員・管理者：情報抽出-学生のアクセスログ一覧 | TBD | 2022-08-11 |  | 2022-08-11 | [6 empty] | 1¦ 新しい / New |  | Late
95 | 【-195】(APIの組み込み)職員・管理者：情報抽出-教職カルテダウンロード | TBD | 2022-08-12 | 2022-08-12 | 2022-08-12 | 2022-08-12 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
96 | 【-197】(APIの組み込み)職員・管理者：学生情報-データ集計 | TBD | 2022-08-15 | 2022-08-15 | 2022-08-15 | 2022-08-15 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
97 | 【-308】(APIの組み込み)職員:授業アンケート管理-授業アンケート設定 | TBD | 2022-08-01 | 2022-08-01 | 2022-08-01 | 2022-08-05 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
98 | 【-309】(APIの組み込み)職員:授業アンケート管理-授業アンケート作成・編集 | TBD | 2022-08-02 | 2022-08-02 | 2022-08-02 | 2022-08-23 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
99 | 【-185】(APIの組み込み)教員・職員：異動履歴 | TBD | 2022-08-03 | 2022-08-03 | 2022-08-03 | 2022-08-03 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
100 | 【-245】(APIの組み込み)アクセス履歴-アクセスログ | TBD | 2022-08-04 | 2022-08-04 | 2022-08-04 | 2022-08-04 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
101 | 【-246】(APIの組み込み)アクセス履歴-アクセスログ-詳細 | TBD | 2022-08-05 | 2022-08-05 | 2022-08-05 | 2022-08-05 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
102 | 【-188】(APIの組み込み)職員・管理者：学生情報-指導教員一覧 | TBD | 2022-08-08 | 2022-08-08 | 2022-08-08 | 2022-08-08 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
103 | 【-189】(APIの組み込み)職員・管理者：学生情報-TOEICスコア一覧 | TBD | 2022-08-09 | 2022-08-09 | 2022-08-09 | 2022-08-09 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
104 | 【-190】(APIの組み込み)職員・管理者：学習・教育目標管理-一覧 | TBD | 2022-08-10 | 2022-08-10 | 2022-08-10 | 2022-08-10 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
105 | 【-191】(APIの組み込み)職員・管理者：学習・教育目標管理-学習・教育達成目標 | TBD | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-08-11 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
106 | 【-192】(APIの組み込み)職員・管理者：学習・教育目標管理-学習・教育達成目標授業科目 | TBD | 2022-08-12 | 2022-08-12 | 2022-08-12 | 2022-08-12 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
107 | 【-193】(APIの組み込み)職員・管理者：学習・教育目標管理-評価項目 | TBD | 2022-08-15 | 2022-08-15 | 2022-08-15 | 2022-08-15 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
108 | 【-194】(APIの組み込み)職員・管理者：学習・教育目標管理-評価基準 | TBD | 2022-08-16 | 2022-08-16 | 2022-08-16 | 2022-08-16 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
109 | 【-210】(APIの組み込み)管理者：システム構築管理-システム設定 | TBD | 2022-08-16 | 2022-08-16 | 2022-08-16 | 2022-08-16 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
110 | 【-211】(APIの組み込み)管理者：システム構築管理-使用言語 | TBD | 2022-08-17 | 2022-08-17 | 2022-08-17 | 2022-08-17 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
111 | 【-212】(APIの組み込み)管理者：システム構築管理-所属項目 | TBD | 2022-08-18 | 2022-08-18 | 2022-08-18 | 2022-08-18 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
112 | 【-213】(APIの組み込み)管理者：システム構築管理-権限 | TBD | 2022-08-19 | 2022-08-19 | 2022-08-19 | 2022-08-19 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
113 | 【-215】(APIの組み込み)管理者：システム構築管理-自動インポート | TBD | 2022-08-22 | 2022-08-22 | 2022-08-22 | 2022-08-22 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
114 | 【-221】(APIの組み込み)管理者：ユーザー管理-学部生、詳細 | TBD | 2022-08-23 | 2022-08-23 | 2022-08-23 | 2022-08-23 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
115 | 【-224】(APIの組み込み)管理者：ユーザー管理-教員 | TBD | 2022-08-24 | 2022-08-24 | 2022-08-24 | 2022-08-24 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
116 | 【-225】(APIの組み込み)管理者：ユーザー管理-職員 | TBD | 2022-08-25 | 2022-08-25 | 2022-08-25 | 2022-08-25 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
117 | 【-325】(APIの組み込み)管理者：ユーザー管理-一般 | TBD | 2022-08-26 | 2022-08-26 | 2022-08-26 | 2022-08-26 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
118 | 【-335】(APIの組み込み)管理者：ユーザー管理-管理者 | TBD | 2022-08-29 | 2022-08-29 | 2022-08-29 | 2022-08-29 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
119 | 【-227】(APIの組み込み)管理者：ユーザー管理-指導教員 | TBD | 2022-08-30 | 2022-08-30 | 2022-08-30 | 2022-08-30 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
120 | 【-228】(APIの組み込み)管理者：ユーザー管理-副担当教員 | TBD | 2022-08-16 | 2022-08-16 | 2022-08-16 | 2022-08-16 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
121 | 【-333】(APIの組み込み)管理者：ユーザー管理-サポート教員 | TBD | 2022-08-17 | 2022-08-17 | 2022-08-17 | 2022-08-17 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
122 | 【-230】(APIの組み込み)管理者：ユーザー管理-ログイン認証 | TBD | 2022-08-18 | 2022-08-18 | 2022-08-18 | 2022-08-18 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
123 | 【-216】(APIの組み込み)管理者：システム構築管理-自動インポート-詳細 | TBD | 2022-08-19 | 2022-08-19 | 2022-08-19 | 2022-08-19 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
124 | 【-348】(APIの組み込み)管理者:学生デフォルト設定 | TBD | 2022-08-22 | 2022-08-22 | 2022-08-22 | 2022-08-22 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
125 | 【-352】(APIの組み込み)管理者:教員の学生デフォルト設定 | TBD | 2022-08-23 | 2022-08-23 | 2022-08-23 | 2022-08-23 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
126 | 【-353】(APIの組み込み)管理者:職員の学生デフォルト設定 | TBD | 2022-08-24 | 2022-08-24 | 2022-08-24 | 2022-08-24 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
127 | 【-217】(APIの組み込み)管理者：所属管理-学部 | TBD | 2022-08-25 | 2022-08-25 | 2022-08-25 | 2022-08-25 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
128 | 【-218】(APIの組み込み)管理者：所属管理-学科 | TBD | 2022-08-26 | 2022-08-26 | 2022-08-26 | 2022-08-26 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
129 | 【-219】(APIの組み込み)管理者：所属管理-コース | TBD | 2022-08-29 | 2022-08-29 | 2022-08-29 | 2022-08-29 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
130 | 【-220】(APIの組み込み)管理者：所属管理-配属先所属 | TBD | 2022-08-30 | 2022-08-30 | 2022-08-30 | 2022-08-30 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
131 | 【-231】(APIの組み込み)管理者：授業項目・成績管理-授業科目 | TBD | 2022-08-31 | 2022-08-31 | 2022-08-31 | 2022-08-31 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
132 | 【-233】(APIの組み込み)管理者：授業項目・成績管理-成績 | TBD | 2022-08-17 | 2022-08-17 | 2022-08-17 | 2022-08-17 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
133 | 【-234】(APIの組み込み)管理者：授業項目・成績管理-成績GPA累計一覧 | TBD | 2022-08-18 | 2022-08-18 | 2022-08-18 | 2022-08-18 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
134 | 【-235】(APIの組み込み)管理者：授業項目・成績管理-自己評価達成度 | TBD | 2022-08-19 | 2022-08-19 | 2022-08-19 | 2022-08-19 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
135 | 【-190】(APIの組み込み)職員・管理者：学習・教育目標管理-一覧 | TBD | 2022-08-22 | 2022-08-22 | 2022-08-22 | 2022-08-22 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
136 | 【-191】(APIの組み込み)職員・管理者：学習・教育目標管理-学習・教育達成目標 | TBD | 2022-08-22 | 2022-08-22 | 2022-08-22 | 2022-08-22 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
137 | 【-192】(APIの組み込み)職員・管理者：学習・教育目標管理-学習・教育達成目標授業科目 | TBD | 2022-08-22 | 2022-08-22 | 2022-08-22 | 2022-08-22 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
138 | 【-193】(APIの組み込み)職員・管理者：学習・教育目標管理-評価項目 | TBD | 2022-08-22 | 2022-08-22 | 2022-08-22 | 2022-08-22 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
139 | 【-194】(APIの組み込み)職員・管理者：学習・教育目標管理-評価基準 | TBD | 2022-08-23 | 2022-08-23 | 2022-08-23 | 2022-08-23 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
140 | 【-236】(APIの組み込み)職員・管理者：学習・教育目標管理-プログラム設定 | TBD | 2022-08-23 | 2022-08-23 | 2022-08-23 | 2022-08-23 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
141 | 【-330】(APIの組み込み)管理者:達成管理-達成設定 | TBD | 2022-08-23 | 2022-08-23 | 2022-08-23 | 2022-08-23 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
142 | 【-331】(APIの組み込み)管理者:達成管理-学習・教育達成目標計算設定 | TBD | 2022-08-24 | 2022-08-24 | 2022-08-24 | 2022-08-24 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
143 | 【-332】(APIの組み込み)管理者:達成管理-学習・教育達成目標授業科目計算設定 | TBD | 2022-08-25 | 2022-08-25 | 2022-08-25 | 2022-08-25 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
144 | 【-237】(APIの組み込み)管理者：自己評価管理-入力スケジュール | TBD | 2022-08-23 | 2022-08-23 | 2022-08-23 | 2022-08-23 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
145 | 【-238】(APIの組み込み)管理者：自己評価管理-自己評価設定 | TBD | 2022-08-24 | 2022-08-24 | 2022-08-24 | 2022-08-24 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
146 | 【-329】(APIの組み込み)管理者：モジュール説明設定 | TBD | 2022-08-25 | 2022-08-25 | 2022-08-25 | 2022-08-25 | [5 empty] | 3 ¦ 終了 / Finished |  | Done
147 | 【-165】(APIの組み込み)ログイン-シングルサインオン | TBD | 2022-08-29 |  | 2022-08-29 | [6 empty] | 1¦ 新しい / New |  | Late
148 | 【-166】(APIの組み込み)ログイン-シボレス | TBD | 2022-08-30 |  | 2022-08-30 | [6 empty] | 1¦ 新しい / New |  | Late
149 | 【-168】(APIの組み込み)ログアウト-ポータルに戻る | TBD | 2022-08-31 | 2022-09-05 | 2022-08-31 | [6 empty] | 2 ¦ 作業中 / In Progress |  | Late
Create UT Checklist
150 | 【-701】[UTC][バッチ詳細]「2達成度の確認」でバッチ処理している計算方法を積み上げ式計算に変更する。 | TBD | 2022-08-15 | 2022-08-15 | 2022-08-15 | 2022-08-15 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
151 | 【-702】[UTC][バッチ詳細]バッチ処理の変更・追加処理 | TBD | 2022-08-15 | 2022-08-15 | 2022-08-15 | 2022-08-15 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
152 | 【-703】[UTC][バッチ詳細] 1 ms_student.csv | TBD | 2022-08-19 | 2022-08-19 | 2022-08-22 | 2022-08-22 | 26 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
153 | 【-704】[UTC][バッチ詳細] 2 ms_teacher.csv | TBD | 2022-08-22 | 2022-08-22 | 2022-08-23 | 2022-08-23 | 26 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
154 | 【-705】[UTC][バッチ詳細] 3 ms_supervisor.csv | TBD | 2022-08-23 | 2022-08-23 | 2022-08-24 | 2022-08-24 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
155 | 【-706】[UTC][バッチ詳細] 4 ms_subject.csv | TBD | 2022-08-24 | 2022-08-24 | 2022-08-25 | 2022-08-25 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
156 | 【-707】[UTC][バッチ詳細] 5 ms_school_record.csv | TBD | 2022-08-25 | 2022-08-25 | 2022-08-26 | 2022-08-26 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
157 | 【-708】[UTC][バッチ詳細] 6 ms_school_record_failure.csv | TBD | 2022-08-26 | 2022-08-26 | 2022-08-29 | 2022-08-29 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
158 | 【-709】[UTC][バッチ詳細] 7 ms_school_record_gpa.csv | TBD | 2022-08-29 | 2022-08-29 | 2022-08-30 | 2022-08-30 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
159 | 【-710】[UTC][バッチ詳細] 8 ms_jikanwari.csv | TBD | 2022-08-30 | 2022-08-30 | 2022-08-31 | 2022-08-31 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
160 | 【-711】[UTC][バッチ詳細] 9 ms_attendance_management.csv | TBD | 2022-08-31 | 2022-08-31 | 2022-09-05 | 2022-09-05 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
161 | 【-712】[UTC][バッチ詳細] 10 圧縮 | TBD | 2022-09-05 | 2022-09-05 | 2022-09-06 | 2022-09-06 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
162 | 【-713】[UTC][バッチ詳細] 11 容量チェック | TBD | 2022-09-06 | 2022-09-06 | 2022-09-07 | 2022-09-07 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
163 | 【-714】[UTC][バッチ詳細] 12 ファイル転送 | TBD | 2022-09-07 | 2022-09-07 | 2022-09-08 | 2022-09-08 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
164 | 【-715】[UTC][バッチ詳細] 13 プロセス残留チェック | TBD | 2022-09-08 | 2022-09-08 | 2022-09-09 | 2022-09-09 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
165 | 【-716】[UTC][バッチ詳細] 14 tr_student_monthly_belongsテーブルのデータ保存を実行 | TBD | 2022-09-12 | 2022-09-12 | 2022-09-13 | 2022-09-13 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
166 | 【-717】[UTC][バッチ詳細] 15 日ごとにアクセスする学生の総数を記録 | TBD | 2022-09-13 | 2022-09-13 | 2022-09-14 | 2022-09-14 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
167 | 【-186】（UTC）教員・職員・管理者：担当学生一覧 | TBD | 2022-08-01 | 2022-08-01 | 2022-08-01 | 2022-08-01 | 56 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
168 | 【-187】（UTC）教員・職員・管理者：担当学生一覧-教職間メモ | TBD | 2022-08-02 | 2022-08-02 | 2022-08-02 | 2022-08-02 | 15 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
169 | 【-188】（UTC）職員・管理者：学生情報-指導教員一覧 | TBD | 2022-08-03 | 2022-08-03 | 2022-08-03 | 2022-08-03 | 31 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
170 | 【-189】（UTC）職員・管理者：学生情報-TOEICスコア一覧 | TBD | 2022-08-04 | 2022-08-04 | 2022-08-05 | 2022-08-05 | 87 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
171 | 【-190】（UTC）職員・管理者：学習・教育目標管理-一覧 | TBD | 2022-08-05 | 2022-08-05 | 2022-08-08 | 2022-08-08 | 47 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
172 | 【-191】（UTC）職員・管理者：学習・教育目標管理-学習・教育達成目標 | TBD | 2022-08-08 | 2022-08-08 | 2022-08-09 | 2022-08-09 | 84 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
173 | 【-192】（UTC）職員・管理者：学習・教育目標管理-学習・教育達成目標授業科目 | TBD | 2022-08-10 | 2022-08-10 | 2022-08-11 | 2022-08-11 | 79 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
174 | 【-193】（UTC）職員・管理者：学習・教育目標管理-評価項目 | TBD | 2022-08-11 | 2022-08-11 | 2022-08-12 | 2022-08-12 | 87 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
175 | 【-194】（UTC）職員・管理者：学習・教育目標管理-評価基準 | TBD | 2022-08-12 | 2022-08-12 | 2022-08-15 | 2022-08-15 | 82 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
176 | 【-196】（UTC）職員・管理者：情報抽出-学生のアクセスログ一覧 | TBD | 2022-08-15 | 2022-08-15 | 2022-08-16 | 2022-08-16 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
177 | 【-195】（UTC）職員・管理者：情報抽出-教職カルテダウンロード | TBD | 2022-08-16 | 2022-08-16 | 2022-08-17 | 2022-08-17 | 66 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
178 | 【-197】（UTC）職員・管理者：学生情報-データ集計 | TBD | 2022-08-17 | 2022-08-17 | 2022-08-18 | 2022-08-18 | 69 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
179 | 【-308】（UTC）職員:授業アンケート管理-授業アンケート設定 | TBD | 2022-08-18 | 2022-08-18 | 2022-08-19 | 2022-08-19 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
180 | 【-309】（UTC）職員:授業アンケート管理-授業アンケート作成・編集 | TBD | 2022-08-19 | 2022-08-19 | 2022-08-22 | 2022-08-22 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
181 | 【-210】（UTC）管理者：システム構築管理-システム設定 | TBD | 2022-08-22 | 2022-08-22 | 2022-08-23 | 2022-08-23 | 85 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
182 | 【-211】（UTC）管理者：システム構築管理-使用言語 | TBD | 2022-08-23 | 2022-08-23 | 2022-08-24 | 2022-08-24 | 77 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
183 | 【-212】（UTC）管理者：システム構築管理-所属項目 | TBD | 2022-08-24 | 2022-08-24 | 2022-08-24 | 2022-08-24 | 78 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
184 | 【-213】（UTC）管理者：システム構築管理-権限 | TBD | 2022-08-24 | 2022-08-24 | 2022-08-25 | 2022-08-25 | 86 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
185 | 【-215】（UTC）管理者：システム構築管理-自動インポート | TBD | 2022-08-25 | 2022-08-25 | 2022-08-26 | 2022-08-26 | 79 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
186 | 【-216】（UTC）管理者：システム構築管理-自動インポート-詳細 | TBD | 2022-08-26 | 2022-08-26 | 2022-08-29 | 2022-08-29 | 61 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
187 | 【-217】（UTC）管理者：所属管理-学部 | TBD | 2022-08-29 | 2022-08-29 | 2022-08-30 | 2022-08-30 | 82 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
188 | 【-218】（UTC）管理者：所属管理-学科 | TBD | 2022-08-30 | 2022-08-30 | 2022-08-31 | 2022-08-31 | 83 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
189 | 【-219】（UTC）管理者：所属管理-コース | TBD | 2022-08-31 | 2022-08-31 | 2022-09-05 | 2022-09-05 | 79 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
190 | 【-220】（UTC）管理者：所属管理-配属先所属 | TBD | 2022-09-05 | 2022-09-05 | 2022-09-06 | 2022-09-06 | 33 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
191 | 【-221】（UTC）管理者：ユーザー管理-学生、詳細 | TBD | 2022-09-06 | 2022-09-06 | 2022-09-07 | 2022-09-07 | 90 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
192 | 【-224】（UTC）管理者：ユーザー管理-教員 | TBD | 2022-09-07 | 2022-09-07 | 2022-09-08 | 2022-09-08 | 76 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
193 | 【-225】（UTC）管理者：ユーザー管理-職員 | TBD | 2022-09-08 | 2022-09-08 | 2022-09-09 | 2022-09-09 | 76 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
194 | 【-325】（UTC）管理者：ユーザー管理-一般 | TBD | 2022-09-09 | 2022-09-09 | 2022-09-12 | 2022-09-12 | 92 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
195 | 【-335】（UTC）管理者：ユーザー管理-管理者 | TBD | 2022-09-12 | 2022-09-12 | 2022-09-13 | 2022-09-13 | 88 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
196 | 【-227】（UTC）管理者：ユーザー管理-指導教員 | TBD | 2022-09-13 | 2022-09-13 | 2022-09-14 | 2022-09-14 | 76 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
197 | 【-228】（UTC）管理者：ユーザー管理-副担当教員 | TBD | 2022-09-14 | 2022-09-14 | 2022-09-15 | 2022-09-15 | 66 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
198 | 【-333】（UTC）管理者：ユーザー管理-サポート教員 | TBD | 2022-09-15 | 2022-09-15 | 2022-09-16 | 2022-09-16 | 79 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
199 | 【-230】（UTC）管理者：ユーザー管理-ログイン認証 | TBD | 2022-09-16 | 2022-09-16 | 2022-09-19 | 2022-09-19 | 78 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
200 | 【-231】（UTC）管理者：授業項目・成績管理-授業科目 | TBD | 2022-09-19 | 2022-09-19 | 2022-09-20 | 2022-09-20 | 79 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
201 | 【-233】（UTC）管理者：授業項目・成績管理-成績 | TBD | 2022-09-20 | 2022-09-20 | 2022-09-21 | 2022-09-21 | 67 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
202 | 【-234】（UTC）管理者：授業項目・成績管理-成績GPA累計一覧 | TBD | 2022-09-21 | 2022-09-21 | 2022-09-22 | 2022-09-22 | 64 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
203 | 【-235】（UTC）管理者：授業項目・成績管理-自己評価達成度 | TBD | 2022-09-22 | 2022-09-22 | 2022-09-23 | 2022-09-23 | 53 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
204 | 【-236】（UTC）職員・管理者：学習・教育目標管理-プログラム設定 | TBD | 2022-09-23 | 2022-09-23 | 2022-09-26 | 2022-09-26 | 67 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
205 | 【-331】（UTC）管理者:達成管理-学習・教育達成目標計算設定 | TBD | 2022-09-26 | 2022-09-26 | 2022-09-27 | 2022-09-27 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
206 | 【-330】（UTC）管理者:達成管理-達成設定 | TBD | 2022-09-27 | 2022-09-27 | 2022-09-27 | 2022-09-27 | 68 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
207 | 【-332】（UTC）管理者:達成管理-学習・教育達成目標授業科目計算設定 | TBD | 2022-09-28 | 2022-09-28 | 2022-09-28 | 2022-09-28 | 87 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
208 | 【-237】（UTC）管理者：自己評価管理-入力スケジュール | TBD | 2022-09-28 | 2022-09-28 | 2022-09-29 | 2022-09-29 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
209 | 【-238】（UTC）管理者：自己評価管理-自己評価設定 | TBD | 2022-09-29 | 2022-09-29 | 2022-09-30 | 2022-09-30 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
210 | 【-348】（UTC）管理者:学生デフォルト設定 | TBD | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
211 | 【-352】（UTC）管理者:教員の学生デフォルト設定 | TBD | 2022-09-14 | 2022-09-14 | 2022-09-15 | 2022-09-15 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
212 | 【-353】（UTC）管理者:職員の学生デフォルト設定 | TBD | 2022-09-15 | 2022-09-15 | 2022-09-16 | 2022-09-16 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
213 | 【-329】（UTC）【学修自己評価システム】管理者：モジュール説明設定 | TBD | 2022-09-16 | 2022-09-16 | 2022-09-19 | 2022-09-19 | 42 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
214 | 【-164】（UTC）ログイン-アカウント | TBD | 2022-09-19 | 2022-09-19 | 2022-09-20 | 2022-09-20 | 37 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
215 | 【-167】（UTC）ログアウト-ログアウト | TBD | 2022-09-20 | 2022-09-20 | 2022-09-20 | 2022-09-20 | 5 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
216 | 【-165】（UTC）ログイン-シングルサインオン | TBD | 2022-09-20 | 2022-09-20 | 2022-09-21 | 2022-09-21 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
217 | 【-166】（UTC）ログイン-シボレス | TBD | 2022-09-21 | 2022-09-21 | 2022-09-21 | 2022-09-21 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
218 | 【-245】（UTC）アクセス履歴-アクセスログ | TBD | 2022-09-21 | 2022-09-21 | 2022-09-22 | 2022-09-22 | 78 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
219 | 【-246】（UTC）アクセス履歴-アクセスログ-詳細 | TBD | 2022-09-23 | 2022-09-23 | 2022-09-23 | 2022-09-23 | 16 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
220 | 【-352】（UTC）管理者:教員の学生デフォルト設定 | TBD | 2022-09-27 | 2022-09-27 | 2022-09-29 | 2022-09-29 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
221 | 【-353】（UTC）管理者:職員の学生デフォルト設定 | TBD | 2022-09-29 | 2022-09-29 | 2022-09-30 | 2022-09-30 | 91 |  | 0% |  |  | 3 ¦ 終了 / Finished |  | Done
Execute UTC Checklist
222 | 【-701】[UTE][バッチ詳細]「2達成度の確認」でバッチ処理している計算方法を積み上げ式計算に変更する。 | TBD | 2022-09-15 |  | 2022-09-21 |  | 15 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
223 | 【-702】[UTE][バッチ詳細]バッチ処理の変更・追加処理 | TBD | 2022-09-15 |  | 2022-09-21 |  | 15 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
224 | 【-703】[UTE][バッチ詳細] 1 ms_student.csv | TBD | 2022-08-19 | 2022-08-19 | 2022-08-22 | 2022-08-22 | 27 | 27 | 100% | 4 | 0 | 3 ¦ 終了 / Finished |  | Done
225 | 【-704】[UTE][バッチ詳細] 2 ms_teacher.csv | TBD | 2022-08-22 | 2022-08-22 | 2022-08-23 | 2022-08-23 | 27 | 27 | 100% | 1 | 0 | 3 ¦ 終了 / Finished |  | Done
226 | 【-705】[UTE][バッチ詳細] 3 ms_supervisor.csv | TBD | 2022-09-16 |  | 2022-09-21 |  | 27 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
227 | 【-706】[UTE][バッチ詳細] 4 ms_subject.csv | TBD | 2022-09-16 |  | 2022-09-21 |  | 27 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
228 | 【-707】[UTE][バッチ詳細] 5 ms_school_record.csv | TBD | 2022-09-16 |  | 2022-09-21 |  | 27 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
229 | 【-708】[UTE][バッチ詳細] 6 ms_school_record_failure.csv | TBD | 2022-09-16 |  | 2022-09-21 |  | 27 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
230 | 【-709】[UTE][バッチ詳細] 7 ms_school_record_gpa.csv | TBD | 2022-09-16 |  | 2022-09-21 |  | 27 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
231 | 【-710】[UTE][バッチ詳細] 8 ms_jikanwari.csv | TBD | 2022-09-16 |  | 2022-09-21 |  | 27 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
232 | 【-711】[UTE][バッチ詳細] 9 ms_attendance_management.csv | TBD | 2022-08-31 |  | 2022-09-05 |  | 27 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
233 | 【-712】[UTE][バッチ詳細] 10 圧縮 | TBD | 2022-09-05 |  | 2022-09-06 |  | 15 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
234 | 【-713】[UTE][バッチ詳細] 11 容量チェック | TBD | 2022-09-06 | 2022-09-06 | 2022-09-07 | 2022-09-07 | 0 | 0 |  | 0 | 0 | 6 ¦ キャンセル / Canceled | Portfolio | Done
235 | 【-714】[UTE][バッチ詳細] 12 ファイル転送 | TBD | 2022-09-07 | 2022-09-07 | 2022-09-08 | 2022-09-08 | 0 | 0 |  | 0 | 0 | 6 ¦ キャンセル / Canceled | Syllabus | Done
236 | 【-715】[UTE][バッチ詳細] 13 プロセス残留チェック | TBD | 2022-09-08 |  | 2022-09-09 |  | 15 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
237 | 【-716】[UTE][バッチ詳細] 14 tr_student_monthly_belongsテーブルのデータ保存を実行 | TBD | 2022-09-12 |  | 2022-09-13 |  | 15 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
238 | 【-717】[UTE][バッチ詳細] 15 日ごとにアクセスする学生の総数を記録 | TBD | 2022-09-13 |  | 2022-09-14 |  | 15 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
239 | 【-186】（UTE）教員・職員・管理者：担当学生一覧 | TBD | 2022-08-01 | 2022-08-01 | 2022-08-01 | 2022-08-01 | 56 | 56 | 100% | 23 | 20 | 4 ¦ リリース完了 / Release |  | Done
240 | 【-187】（UTE）教員・職員・管理者：担当学生一覧-教職間メモ | TBD | 2022-08-02 | 2022-08-02 | 2022-08-02 | 2022-08-02 | 15 | 15 | 100% | 10 | 9 | 4 ¦ リリース完了 / Release |  | Done
241 | 【-188】（UTE）職員・管理者：学生情報-指導教員一覧 | TBD | 2022-08-03 | 2022-08-03 | 2022-08-03 | 2022-08-03 | 31 | 31 | 100% | 9 | 4 | 4 ¦ リリース完了 / Release |  | Done
242 | 【-189】（UTE）職員・管理者：学生情報-TOEICスコア一覧 | TBD | 2022-08-04 | 2022-08-04 | 2022-08-05 | 2022-08-05 | 87 | 87 | 100% | 5 | 4 | 4 ¦ リリース完了 / Release |  | Done
243 | 【-190】（UTE）職員・管理者：学習・教育目標管理-一覧 | TBD | 2022-08-05 | 2022-08-05 | 2022-08-08 | 2022-08-08 | 47 | 47 | 100% | 18 | 16 | 4 ¦ リリース完了 / Release |  | Done
244 | 【-191】（UTE）職員・管理者：学習・教育目標管理-学習・教育達成目標 | TBD | 2022-08-08 | 2022-08-08 | 2022-08-09 | 2022-08-09 | 84 | 84 | 100% | 13 | 9 | 4 ¦ リリース完了 / Release |  | Done
245 | 【-192】（UTE）職員・管理者：学習・教育目標管理-学習・教育達成目標授業科目 | TBD | 2022-08-10 | 2022-08-10 | 2022-08-11 | 2022-08-11 | 79 | 79 | 100% | 12 | 8 | 4 ¦ リリース完了 / Release |  | Done
246 | 【-193】（UTE）職員・管理者：学習・教育目標管理-評価項目 | TBD | 2022-08-11 | 2022-08-11 | 2022-08-12 | 2022-08-12 | 87 | 87 | 100% | 14 | 10 | 4 ¦ リリース完了 / Release |  | Done
247 | 【-194】（UTE）職員・管理者：学習・教育目標管理-評価基準 | TBD | 2022-08-12 | 2022-08-12 | 2022-08-15 | 2022-08-15 | 82 | 82 | 100% | 6 | 4 | 4 ¦ リリース完了 / Release |  | Done
248 | 【-196】（UTE）職員・管理者：情報抽出-学生のアクセスログ一覧 | TBD | 2022-09-12 |  | 2022-09-12 |  | 91 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
249 | 【-195】（UTE）職員・管理者：情報抽出-教職カルテダウンロード | TBD | 2022-08-16 | 2022-08-16 | 2022-08-17 | 2022-08-17 | 66 | 66 | 100% | 3 | 2 | 4 ¦ リリース完了 / Release |  | Done
250 | 【-197】（UTE）職員・管理者：学生情報-データ集計 | TBD | 2022-08-17 | 2022-08-17 | 2022-08-18 | 2022-08-18 | 69 | 69 | 100% | 1 | 1 | 4 ¦ リリース完了 / Release |  | Done
251 | 【-308】（UTE）職員:授業アンケート管理-授業アンケート設定 | TBD | 2022-09-12 |  | 2022-09-12 |  | 91 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
252 | 【-309】（UTE）職員:授業アンケート管理-授業アンケート作成・編集 | TBD | 2022-09-12 |  | 2022-09-12 |  | 91 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
253 | 【-210】（UTE）管理者：システム構築管理-システム設定 | TBD | 2022-08-22 | 2022-08-22 | 2022-08-23 | 2022-08-23 | 85 | 85 | 100% | 7 | 6 | 4 ¦ リリース完了 / Release |  | Done
254 | 【-211】（UTE）管理者：システム構築管理-使用言語 | TBD | 2022-08-23 | 2022-08-23 | 2022-08-24 | 2022-08-24 | 77 | 77 | 100% | 20 | 18 | 4 ¦ リリース完了 / Release |  | Done
255 | 【-212】（UTE）管理者：システム構築管理-所属項目 | TBD | 2022-08-24 | 2022-08-24 | 2022-08-24 | 2022-08-24 | 78 | 78 | 100% | 15 | 12 | 4 ¦ リリース完了 / Release |  | Done
256 | 【-213】（UTE）管理者：システム構築管理-権限 | TBD | 2022-08-24 | 2022-08-24 | 2022-08-25 | 2022-08-25 | 86 | 86 | 100% | 9 | 7 | 4 ¦ リリース完了 / Release |  | Done
257 | 【-215】（UTE）管理者：システム構築管理-自動インポート | TBD | 2022-08-25 | 2022-08-25 | 2022-08-26 | 2022-08-26 | 79 | 79 | 100% | 5 | 5 | 4 ¦ リリース完了 / Release |  | Done
258 | 【-216】（UTE）管理者：システム構築管理-自動インポート-詳細 | TBD | 2022-08-26 | 2022-08-26 | 2022-08-29 | 2022-08-29 | 61 | 61 | 100% | 0 | 0 | 4 ¦ リリース完了 / Release |  | Done
259 | 【-217】（UTE）管理者：所属管理-学部 | TBD | 2022-08-29 | 2022-08-29 | 2022-08-30 | 2022-08-30 | 82 | 82 | 100% | 2 | 1 | 4 ¦ リリース完了 / Release |  | Done
260 | 【-218】（UTE）管理者：所属管理-学科 | TBD | 2022-08-30 | 2022-08-30 | 2022-08-31 | 2022-08-31 | 83 | 83 | 100% | 5 | 3 | 4 ¦ リリース完了 / Release |  | Done
261 | 【-219】（UTE）管理者：所属管理-コース | TBD | 2022-08-31 | 2022-08-31 | 2022-09-05 | 2022-08-31 | 79 | 79 | 100% | 4 | 3 | 4 ¦ リリース完了 / Release |  | Done
262 | 【-220】（UTE）管理者：所属管理-配属先所属 | TBD | 2022-09-05 | 2022-08-31 | 2022-09-06 | 2022-08-31 | 33 | 33 | 100% | 3 | 3 | 4 ¦ リリース完了 / Release |  | Done
263 | 【-221】（UTE）管理者：ユーザー管理-学生、詳細 | TBD | 2022-09-06 | 2022-09-06 | 2022-09-07 | 2022-09-06 | 90 | 90 | 100% | 5 | 1 | 3 ¦ 終了 / Finished |  | Done
264 | 【-224】（UTE）管理者：ユーザー管理-教員 | TBD | 2022-09-07 | 2022-08-22 | 2022-09-08 | 2022-08-22 | 76 | 76 | 100% | 4 | 2 | 4 ¦ リリース完了 / Release |  | Done
265 | 【-225】（UTE）管理者：ユーザー管理-職員 | TBD | 2022-09-08 | 2022-08-22 | 2022-09-09 | 2022-08-22 | 76 | 76 | 100% | 6 | 4 | 4 ¦ リリース完了 / Release |  | Done
266 | 【-325】（UTE）管理者：ユーザー管理-一般 | TBD | 2022-09-09 | 2022-08-25 | 2022-09-12 | 2022-08-26 | 92 | 92 | 100% | 5 | 3 | 4 ¦ リリース完了 / Release |  | Done
267 | 【-335】（UTE）管理者：ユーザー管理-管理者 | TBD | 2022-09-12 | 2022-08-31 | 2022-09-13 | 2022-08-31 | 88 | 88 | 100% | 5 | 0 | 3 ¦ 終了 / Finished |  | Done
268 | 【-227】（UTE）管理者：ユーザー管理-指導教員 | TBD | 2022-09-13 | 2022-08-19 | 2022-09-14 | 2022-08-19 | 76 | 76 | 100% | 7 | 4 | 4 ¦ リリース完了 / Release |  | Done
269 | 【-228】（UTE）管理者：ユーザー管理-副担当教員 | TBD | 2022-09-14 | 2022-08-22 | 2022-09-15 | 2022-08-22 | 66 | 66 | 100% | 11 | 9 | 4 ¦ リリース完了 / Release |  | Done
270 | 【-333】（UTE）管理者：ユーザー管理-サポート教員 | TBD | 2022-09-15 | 2022-08-30 | 2022-09-16 | 2022-08-30 | 79 | 79 | 100% | 2 | 2 | 4 ¦ リリース完了 / Release |  | Done
271 | 【-230】（UTE）管理者：ユーザー管理-ログイン認証 | TBD | 2022-09-16 | 2022-08-23 | 2022-09-19 | 2022-08-23 | 78 | 78 | 100% | 11 | 9 | 4 ¦ リリース完了 / Release |  | Done
272 | 【-231】（UTE）管理者：授業項目・成績管理-授業科目 | TBD | 2022-09-19 | 2022-08-23 | 2022-09-20 | 2022-08-23 | 79 | 79 | 100% | 6 | 5 | 4 ¦ リリース完了 / Release |  | Done
273 | 【-233】（UTE）管理者：授業項目・成績管理-成績 | TBD | 2022-09-20 | 2022-08-22 | 2022-09-21 | 2022-08-22 | 67 | 67 | 100% | 1 | 1 | 4 ¦ リリース完了 / Release |  | Done
274 | 【-234】（UTE）管理者：授業項目・成績管理-成績GPA累計一覧 | TBD | 2022-09-21 | 2022-08-31 | 2022-09-22 | 2022-08-31 | 64 | 64 | 100% | 1 | 0 | 3 ¦ 終了 / Finished |  | Done
275 | 【-235】（UTE）管理者：授業項目・成績管理-自己評価達成度 | TBD | 2022-09-22 | 2022-08-29 | 2022-09-23 | 2022-08-29 | 53 | 53 | 100% | 7 | 4 | 4 ¦ リリース完了 / Release |  | Done
276 | 【-236】（UTE）職員・管理者：学習・教育目標管理-プログラム設定 | TBD | 2022-09-23 | 2022-09-06 | 2022-09-26 | 2022-09-06 | 67 | 67 | 100% | 3 | 0 | 3 ¦ 終了 / Finished |  | Done
277 | 【-331】（UTE）管理者:達成管理-学習・教育達成目標計算設定 | TBD | 2022-09-26 |  | 2022-09-27 |  | 91 | 0 | 0% | 1 | 0 | 1¦ 新しい / New |  | Late
278 | 【-330】（UTE）管理者:達成管理-達成設定 | TBD | 2022-09-27 | 2022-09-06 | 2022-09-27 | 2022-09-06 | 68 | 68 | 100% | 1 | 0 | 3 ¦ 終了 / Finished |  | Done
279 | 【-332】（UTE）管理者:達成管理-学習・教育達成目標授業科目計算設定 | TBD | 2022-09-28 |  | 2022-09-28 |  | 87 | 87 | 100% | 4 | 0 | 3 ¦ 終了 / Finished |  | Late
280 | 【-237】（UTE）管理者：自己評価管理-入力スケジュール | TBD | 2022-09-28 |  | 2022-09-29 |  | 91 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
281 | 【-238】（UTE）管理者：自己評価管理-自己評価設定 | TBD | 2022-09-29 |  | 2022-09-30 |  | 91 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
282 | 【-348】（UTE）管理者:学生デフォルト設定 | TBD | 2022-09-30 |  | 2022-09-30 |  | 91 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
283 | 【-352】（UTE）管理者:教員の学生デフォルト設定 | TBD | 2022-09-14 |  | 2022-09-15 |  | 91 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
284 | 【-353】（UTE）管理者:職員の学生デフォルト設定 | TBD | 2022-09-15 |  | 2022-09-16 |  | 91 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
285 | 【-329】（UTE）【学修自己評価システム】管理者：モジュール説明設定 | TBD | 2022-09-16 | 2022-08-24 | 2022-09-19 | 2022-08-24 | 42 | 42 | 100% | 3 | 3 | 3 ¦ 終了 / Finished |  | Done
286 | 【-164】（UTE）ログイン-アカウント | TBD | 2022-09-19 | 2022-08-04 | 2022-09-20 | 2022-08-04 | 37 | 37 | 100% | 8 | 7 | 3 ¦ 終了 / Finished |  | Done
287 | 【-167】（UTE）ログアウト-ログアウト | TBD | 2022-09-20 | 2022-08-05 | 2022-09-20 | 2022-08-05 | 5 | 5 | 100% | 0 | 0 | 3 ¦ 終了 / Finished |  | Done
288 | 【-165】（UTE）ログイン-シングルサインオン | TBD | 2022-09-20 |  | 2022-09-21 |  | 91 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
289 | 【-166】（UTE）ログイン-シボレス | TBD | 2022-09-21 |  | 2022-09-21 |  | 91 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
290 | 【-245】（UTE）アクセス履歴-アクセスログ | TBD | 2022-09-21 | 2022-08-17 | 2022-09-22 | 2022-08-17 | 78 | 78 | 100% | 3 | 2 | 4 ¦ リリース完了 / Release |  | Done
291 | 【-246】（UTE）アクセス履歴-アクセスログ-詳細 | TBD | 2022-09-23 | 2022-08-18 | 2022-09-23 | 2022-08-18 | 16 | 16 | 100% | 0 | 0 | 4 ¦ リリース完了 / Release |  | Done
292 | 【-352】（UTE）管理者:教員の学生デフォルト設定 | TBD | 2022-09-27 |  | 2022-09-29 |  | 91 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
293 | 【-353】（UTE）管理者:職員の学生デフォルト設定 | TBD | 2022-09-29 |  | 2022-09-30 |  | 91 | 0 | 0% | 0 | 0 | 1¦ 新しい / New |  | Late
Note on A156: @anhduy.le1997@gmail.com Fill data UTC/UTR _Assigned to Duy Lê Anh_ -An Nguyen
Note on A229: @anhduy.le1997@gmail.com Fill data ở phần UTC/UTR _Assigned to Duy Lê Anh_ -An Nguyen

## 99.Config (hidden)
Status
新しい | 1¦ 新しい / New
作業中 | 2 ¦ 作業中 / In Progress
終了 | 3 ¦ 終了 / Finished
リリース完了 | 4 ¦ リリース完了 / Release
保留中 | 5 ¦ 保留中 / Pending
キャンセル | 6 ¦ キャンセル / Canceled

## SetHoliday (hidden)
2022-01-03
2022-01-31
2022-09-01
2022-09-02

## Data (hidden)
Burn down task
Total Task | 0
Day | 2022-06-30 | 2022-07-01 | 2022-07-02 | 2022-07-03 | 2022-07-04 | 2022-07-05 | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-09 | 2022-07-10 | 2022-07-11 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15 | 2022-07-16 | 2022-07-17 | 2022-07-18 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-24 | 2022-07-25 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-07-30 | 2022-07-31 | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13 | 2022-08-14 | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-20 | 2022-08-21 | 2022-08-22 | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-26 | 2022-08-27 | 2022-08-28 | 2022-08-29 | 2022-08-30 | 2022-08-31 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-04 | 2022-09-05
予定に毎日完成済作業 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
予定に残作業 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
実際に毎日完成済作業 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
実際に残作業 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
現在の日付 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0